## Sheet1
NO | TASK | DESCRIPTION | STATUS | ETA
1 | Change SIP trunk from old system to new system | GMSC forward call to new system: missed call, emergency call, call to 154, call to 119 | Pending
2 | Change SMSC account test to real | Change SMSC account test to real | Pending
3 | Export current active subscriber from old system | Export current active subscriber from old system: - Voicemail - MCA - Voicemail + MCA - NotifyMe Information contains: - ISDN - Register time - Package type (MCA/VM/MCA+MV/Notify Me) | Pending
4 | Import subscriber to new system | Import subscriber to new system: - Voicemail - MCA - Voicemail + MCA - NotifyMe | Pending
5 | Test after swap | Test after swap | Pending