## Milestone Chart
Service Migration to MPS (CP not connected) | [9 empty] | PARTNER
CP NAME
Process | Item | Considerations | N° | Milestone | Description | In Charge (MPS Team) | Coordinate | Working Days - CP | Working Days - Bitel | Progress Review | Deadline
Integration | Connect service to MPS | 1) Partner is not connected to Bitel (MPS or other) | 1 | Kick-Off | BITEL task: Step 01: - Share Documentation - Create Group to start coordinations. Step 02: - Technical kick-off meeting: -Present the Platform, adress its flows for Subscription, Renewal, Charging along different channels. CP task: -CP Shares service profile: Pricing, SMS Scenario, Subscription frequency, etc. Make checklist: Important. Review all possible cases that may place the integration at risk | MPS Team | CP | 1 | 1
|  |  | 2 | Connection | BITEL/CP Connection stablishment among BITEL-CP (VPN) -Testing and troubleshooting if needed. | MPS Team | Transmission Dpt (VTP) Transmission Dpt (VTNet) | 10 | 10
|  |  | 3 | Service Creation | SMS FLOW: BITEL: Service Creation in MPS platform under testing SC: -CP/Service/Subservice creation -Pricing/Charging configuration -SMS Scenario configuration -Policies configuration. CP: -Interfaces development (API) BITEL/CP: Step-by-Step testing and troubleshooting. Final SMS technical flow testing. | MPS Team | CP | 25 | 5
[5 empty] | WAP FLOW: CP: -WAP interface development (API) BITEL: -Wap flow configuration. -Coordination and step-by-step testing with BITEL. BITEL/CP: Step-by-Step testing and troubleshooting. Final WAP technical flow testing | MPS Team | CP |  | 5
|  |  | 4 | Migration (If needed) | BITEL: -Requirement of full detailed service's customer base to Kinetic. -Customer's base insertion to Bitel's DB. -Service disablement from Kinetic. -SC configuration to point to MPS CP: -Configures service to point to MPS | MPS Team | CP | 1 | 1
|  |  | 5 | Testing | Full Service testing and approval | Audit Company | VAS Commercial Team | 1 | 1
[6 empty] | TOTAL |  | 38 | 23